## Sheet1
STEP I (RFQ) Estimated Time Line |  |  | BOR Requirements
a. Owner issues public advertisement of RFQ | 2017-01-04 | -----
b. Deadline for written questions/requests for clarification (see Section 6). | 2017-01-13 | 4:00pm | issue addenda response at least 7 days prior to submission date (post response by the 5th due to holidays)
c. Deadline for submission of Statements of Qualifications | 2017-01-25 | 2:00pm | at least 21 days after posting date
d. Owner completes evaluation, post results, and issues notification to finalist firms | 2017-02-01 | ----- | recommended 7 day review period
e. Owner conducts Mandatory Pre-Proposal Site Visit for finalists | 2017-02-08 | TBD | at least one week after notification
f. Deadline for finalist submission of written questions and requests for clarification | 2017-02-15 | 14:00 | at least one week from site visit (allow 5 days for responses)
g. Deadline for submission of Design Team Proposals | 2017-03-01 | 14:00 | at least one week from Q&A
h. Owner interviews finalist firms and Fee Proposals are due | 2017-03-08 | TBA | at least one week from receipt of proposals
INSTRUCTIONS FOR USE:
Hi Kim,
Please see attached. The trick is to use this as just a starting point. You change the first date to the posting date that you wish and all the dates adjust accordingly to the BOR prescribed/recommended dates. You have to manually review the calendar and check each sequential date to confirm that they fit you specific project needs and that dates don’t land on a weekend or on a Monday for Submittals.
As a tool it is a good one to at least help start the schedule and get everything aligned and then you can move each date on your actual RFQ to accommodate the specific realities.
Thank you for setting up the original and sharing it with me.
Chris Sanders